## Capex 24-25
No. | Project Name | Budget Amount | Procurement Method | Descipline (Supplies/Services / Works) | Priority of Procurement | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
1 | Indoor Aircon Units Replacement - Tshomarelo | 6000000 | Open Domestic Bidding | Works | 1 - Highly Critical | 2024-04-05 | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-07-31 | 2024-08-30
2 | Laptops | 500000 | Open Domestic Bidding | Supplies | 1 - Highly Critical | 2024-04-05 | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-06-28 | N/A
3 | Coin Counting Machine | 63000 | Quotations Proposal | Supplies | 2 - Critical | 2024-04-12 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-26 | 2024-04-30 | 2024-05-24 | N/A
4 | Bulk note counting machine | 150000 | Quotations Proposal | Supplies | 2 - Critical | 2024-04-12 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-26 | 2024-04-30 | 2024-05-24 | N/A
5 | Speaker | 7200 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-04-12 | 2024-04-17 | 2024-04-19 | 2024-04-24 | 2024-04-26 | 2024-04-30 | 2024-05-08 | N/A
6 | Finacle Enhancement (New Products) | 1700000 | Open Domestic Bidding | Services | 1 - Highly Critical | 2024-04-19 | 2024-05-03 | 2024-05-10 | 2024-05-15 | 2024-05-22 | 2024-05-28 | 2024-09-27 | 2024-10-31
7 | Fiber Switches | 800000 | Open Domestic Bidding | Services | 1 - Highly Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-12 | 2024-08-23 | N/A
8 | BankWorld HA & DR setup | 600000 | Selective Bidding | Supplies | 1 - Highly Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-12 | 2024-08-23 | N/A
9 | Agency Banking App | 4000000 | Open Domestic Bidding | Services | 1 - Highly Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-27 | 2024-05-31 | 2024-06-07 | 2024-08-30 | 2024-09-27
10 | Network Detection and Response | 1000000 | Selective Bidding | Services | 2 - Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-27 | 2024-05-31 | 2024-06-07 | 2024-08-30 | 2024-09-27
11 | Digital Risk Management Solution (GAP Analysis) | 500000 | Selective Bidding | Services | 2 - Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-27 | 2024-05-31 | 2024-06-07 | 2024-08-30 | 2024-09-27
12 | Digital Risk Protection and attack Surface Management | 400000 | Open Domestic Bidding | Services | 2 - Critical | 2024-04-26 | 2024-05-15 | 2024-05-22 | 2024-05-27 | 2024-05-31 | 2024-06-07 | 2024-08-30 | 2024-09-27
13 | Removal of Basement Foundation - Tshomarelo | 150000 | Quotations Proposal | Works | 3 - Less Critical | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-22 | 2024-05-29 | 2024-06-07 | 2024-07-31 | 2024-08-30
14 | BankWorld Upgrade | 4700000 | Selective Bidding | Services | 1 - Highly Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-31 | 2024-08-30 | 2024-09-27
15 | TeamFlect Corporate Performance Management | 50000 | Quotations Proposal | Services | 2 - Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-31 | 2024-07-31 | 2024-08-30
16 | Shredding Machine | 80000 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-29 | 2024-06-07 | N/A
17 | Gazebbos Chair | 6300 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-29 | 2024-06-07 | N/A
18 | Gazebbos table | 10500 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-29 | 2024-06-07 | N/A
19 | Television set | 90000 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-29 | 2024-06-07 | N/A
20 | UV light machines | 66500 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-05-10 | 2024-05-15 | 2024-05-17 | 2024-05-21 | 2024-05-24 | 2024-05-29 | 2024-06-07 | N/A
21 | Card Issuing Capabilities (New Card Bins, Prepaid Card, Credit Card, Card Stock) | 2400000 | Open Domestic Bidding | Supplies | 2 - Critical | 2024-05-31 | 2024-08-07 | 2024-08-14 | 2024-08-19 | 2024-08-26 | 2024-08-30 | 2024-12-06 | 2024-12-31
22 | Loan Application Management System | 1200000 | Selective Bidding | Services | 2 - Critical | 2024-06-03 | 2024-06-14 | 2024-06-20 | 2024-06-26 | 2024-07-05 | 2024-07-12 | 2024-10-31 | 2024-11-29
23 | Office Redesign (Internal Audit) | 200000 | Quotations Proposal | Works | 3 - Less Critical | 2024-06-07 | 2024-06-14 | 2024-06-21 | 2024-06-26 | 2024-07-04 | 2024-07-10 | 2024-09-27 | 2024-10-25
24 | Printers | 100000 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-04 | 2024-07-11 | 2024-07-18 | 2024-07-31 | N/A
25 | Reconcilliations System software | 2500000 | Open Domestic Bidding | Services | 2 - Critical | 2024-06-14 | 2024-06-28 | 2024-07-05 | 2024-07-10 | 2024-07-19 | 2024-07-26 | 2024-10-31 | 2024-11-29
26 | Servers | 800000 | Open Domestic Bidding | Supplies | 2 - Critical | 2024-07-05 | 2024-07-24 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-20 | 2024-09-25 | N/A
27 | Projector | 40500 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-07-05 | 2024-07-12 | 2024-07-19 | 2024-07-24 | 2024-07-30 | 2024-08-02 | 2024-08-09 | N/A
28 | Note Counting Machine | 385000 | Open Domestic Bidding | Supplies | 3 - Less Critical | 2024-07-05 | 2024-07-24 | 2024-08-02 | 2024-08-07 | 2024-08-14 | 2024-08-16 | 2024-09-13 | N/A
29 | Gym Extension - Tshomarelo | 100000 | Quotations Proposal | Works | 3 - Less Critical | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-21 | 2024-08-28 | 2024-09-06 | 2024-10-11 | 2024-11-08
30 | POS devices | 500000 | Open Domestic Bidding | Supplies & Services | 2 - Critical | 2024-08-02 | 2024-08-16 | 2024-08-23 | 2024-08-28 | 2024-09-04 | 2024-09-09 | 2024-11-29 | 2024-12-31
31 | Automation (CBS and ERP) | 500000 | Open Domestic Bidding | Services | 1 - Highly Critical | 2024-08-09 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-12-31 | 2025-01-31
32 | E KYC Solution | 600000 | Selective Bidding | Services | 2 - Critical | 2024-08-23 | 2024-09-06 | 2024-09-13 | 2024-09-18 | 2024-09-25 | 2024-10-04 | 2024-11-29 | 2024-12-31
33 | Database Activity Monitoring and Database Firewall | 1000000 | Open Domestic Bidding | Services | 2 - Critical | 2024-08-30 | 2024-09-13 | 2024-09-20 | 2024-09-25 | 2024-10-04 | 2024-10-11 | 2024-12-31 | 2025-01-31
34 | API Enablements | 1000000 | Open Domestic Bidding | Services | 2 - Critical | 2024-09-13 | 2024-09-27 | 2024-10-04 | 2024-10-09 | 2024-10-16 | 2024-10-22 | 2025-02-07 | 2025-03-07
35 | Routers & Switches | 600000 | Open Domestic Bidding | Supplies | 2 - Critical | 2024-10-04 | 2024-10-18 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-11-15 | 2024-12-06 | N/A
36 | Server Room Monitoring | 750000 | Open Domestic Bidding | Services | 2 - Critical | 2024-10-04 | 2024-10-18 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-11-15 | 2024-12-06 | N/A
37 | Gazebbos Burner | 400000 | Open Domestic Bidding | Supplies | 3 - Less Critical | 2024-10-04 | 2024-10-18 | 2024-10-25 | 2024-10-30 | 2024-11-07 | 2024-11-12 | 2024-11-26 | N/A
38 | Water Dispenser | 27000 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-11-08 | 2024-11-13 | 2024-11-14 | 2024-11-19 | 2024-11-22 | 2024-11-25 | 2024-11-29 | N/A
39 | Office Desk | 100000 | Quotations Proposal | Supplies | 3 - Less Critical | 2024-11-08 | 2024-11-13 | 2024-11-14 | 2024-11-19 | 2024-11-22 | 2024-11-25 | 2024-11-29 | N/A
40 | Office Chairs | 300000 | Open Domestic Bidding | Supplies | 3 - Less Critical | 2024-12-06 | 2024-12-20 | 2025-01-10 | 2025-01-15 | 2025-01-21 | 2025-01-23 | 2025-01-30 | N/A
41 | USSD project roll over | 1500000 | Direct Procurement | Services | 2 - Critical | 2024-09-13: Project Rollover - Implementation
| Total | 35876000
LEGEND
1 - Highly Critical
2 - Critical
3 - Less Critical

## Spend Charts
Project Name | Budget Amount | Actual Cost to Date
Water Proofing | 500000 | 295, 300.00
Project/construction Supervision | 960000 | 98401.19
Office Equipment (Assorted) | 73500 | 71, 342.00
Total Budget | 39336929.24 | 1, 211, 413.19

## PP (Capital Expenditure)
PROCUREMENT PLAN FINANCIAL YEAR 2023/2024
FINANCIAL YEAR: 2023 / 2024
Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
Water Proofing | 500000 | Water Proofing | Selective | Works | 500000 | 2023-04-04 | 14 April 2023 | 19 April 2023 | 21 April 2023 | 25 April 2023 | 26 April 2021 | 19 May 2023 | 27 May 2023
Thermal Inspections and Earth Connections | 1200000 | Thermal Inspections and Earth Connections | Open Domestic Bidding | Service | 1200000 | 2023-08-11 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-20 | 2023-09-21 | 2023-10-13 | 2023-10-20
Aircon Chilla Pipe | 5000000 | Aircon Chilla Pipe | Selective | Works | 5000000 | On-going | N/A | N/A | N/A | N/A | N/A | 2023-09-30 | 06 October 2023
Project/construction Supervision | 960000 | Project/construction Supervision | Selective | Service | 960000 | On-going | N/A | N/A | N/A | N/A | N/A | 2023-09-30 | 06 October 2023
Re-design of the upper outside parking shade | 680000 | Re-design of the upper outside parking shade | Open Domestic Bidding | Works | 680000 | 2023-05-01 | 26 May 2023 | 31 May 2023 | 01 June 2023 | 03 June 2023 | 05 June 2023 | 24 June 2023 | 30 June 2023
Fire Suppresion System | 500000 | Fire Suppresion System | Open Domestic Bidding | Works | 500000 | 2023-07-03 | 28 July 2023 | 02 August 2023 | 04 August 2023 | 09 August 2023 | 25 August 2023 | 08 September 2023 | 15 September 2023
Fleet - Pool | 2432929.24 | Fleet - Pool | Selective | Supplies | 2432929.24 | 2023-06-02 | 16 June 2023 | 20 June 2023 | 22 June 2023 | 26 June 2023 | 27 June 2023 | 21 July 2023 | 28 July 2023
Fleet - Directors | 4750000 | Fleet - Directors | Selective | Supplies | 4750000 | 2023-06-02 | 16 June 2023 | 20 June 2023 | 22 June 2023 | 26 June 2023 | 27 June 2023 | 04 August 2023 | 11 August 2023
Laptops | 300000 | Laptops | Quotations Proposal | Supplies | 300000 | 2023-05-12 | 2023-05-26 | 31 May 2023 | 02 June 2023 | 06 June 2023 | 07 June 2023 | 07 July 2023 | 14 July 2023
PC New | 250000 | PC New | Quotations Proposal | Supplies | 250000 | 2023-05-12 | 2023-05-26 | 31 May 2023 | 02 June 2023 | 06 June 2023 | 07 June 2023 | 07 July 2023 | 14 July 2023
Biometric access controls | 3500000 | Biometric access controls | Open Domestic Bidding | Works | 3500000 | 2023-07-03 | 28 July 2023 | 02 August 2023 | 04 August 2023 | 09 August 2023 | 25 August 2023 | 08 September 2023 | 15 September 2023
Wireless/Mobile Copiers | 16000 | Wireless/Mobile Copiers | Micro procurement | Supplies | 16000 | 2023-11-03 | 01 December 2023 | 06 December 2023 | 08 December 2023 | 13 December 2023 | 28 December 2023 | 26 January 2024 | 02 February 2024
Cisco 9300 Switches | 500000 | Cisco 9300 Switches | Quotations Proposal | Works | 500000 | 2023-07-10 | 04 August 2023 | 09 August 2023 | 11 August 2023 | 16 August 2023 | 29 August 2023 | 29 September 2023 | 06 October 2023
Instant Card Printer | 700000 | Instant Card Printer | Open Domestic Bidding | Supplies | 700000 | 2023-11-03 | 01 December 2023 | 06 December 2023 | 08 December 2023 | 13 December 2023 | 28 December 2023 | 26 January 2024 | 02 February 2024
SDWAN Implementation | 3000000 | SDWAN Implementation | Open Domestic Bidding | Services | 3000000 | 2023-07-10 | 04 August 2023 | 09 August 2023 | 11 August 2023 | 16 August 2023 | 29 August 2023 | 29 September 2023 | 06 October 2023
Parameter Firewall | 1000000 | Parameter Firewall | Selective | Services | 1000000 | 2023-07-10 | 04 August 2023 | 09 August 2023 | 11 August 2023 | 16 August 2023 | 29 August 2023 | 29 September 2023 | 06 October 2023
Vehicle Tracking and Management | 200000 | Vehicle Tracking and Management | Quotations Proposal | Services | 200000 | 2023-06-09 | 22 June 2023 | 27 June 2023 | 28 June 2023 | 29 June 2023 | 05 July 2023 | 28 July 2023 | 05 July 2023
TEAMMATE | 330000 | TEAMMATE | Open International Bidding | Services | 330000 | 2023-04-10 | 12 May 2023 | 16 May 2023 | 18 May 2023 | 22 May 2023 | 09 June 2023 | 23 June 2023 | 30 June 2023
USSD (Mobile Banking) | 4200000 | USSD (Mobile Banking) | Selective | Services | 4200000 | 2023-04-03 | 14 April 2023 | 19 April 2023 | 21 April 2023 | 25 April 2023 | 15 May 2023 | 15 August 2023 | 22 August 2023
Bankworld - Business Continuity | 3800000 | Bankworld - Business Continuity | Open Domestic Bidding | Services | 3800000 | 2023-08-01 | 31 August 2023 | 06 September 2023 | 08 September 2023 | 13 September 2023 | 28 September 2023 | 13 October 2023 | 20 October 2023
CR2 - Digital Banking | 500000 | CR2 - Digital Banking | Direct Procurement | Services | 500000 | 2023-12-01 | 15 December 2023 | 19 December 2023 | 21 December 2023 | 28 December 2023 | 2024-01-01 | 12 January 2024 | 19 January 2024
Contact Centre Software | 1200000 | Contact Centre Software | Direct Procurement | Services | 1200000 | On-going | N/A | N/A | N/A | N/A | 17 April 2023 | 28 April 2023 | 5 May 2023
CRM | 1000000 | CRM | Restricted International Bidding | Services | 1000000 | 2023-09-15 | 13 October 2023 | 18 October 2023 | 20 October 2023 | 25 October 2023 | 15 November 2023 | 15 December 2023 | 22 December
Visa Risk Manager | 800000 | Visa Risk Manager | Selective | Services | 800000 | 2023-11-03 | 17 November 2023 | 23 November 2023 | 24 November 2023 | 29 November 2023 | 15 December 2023 | 15 January 2024 | 19 January 2024
Network Access Control | 500000 | Network Access Control | Open Domestic Bidding | Works | 500000 | 2023-07-03 | 28 July 2023 | 02 August 2023 | 04 August 2023 | 09 August 2023 | 25 August 2023 | 08 September 2023 | 15 September 2023
Identity and Access Management | 500000 | Identity and Access Management | Open Domestic Bidding | Services | 500000 | 2023-07-03 | 28 July 2023 | 02 August 2023 | 04 August 2023 | 09 August 2023 | 25 August 2023 | 08 September 2023 | 15 September 2023
Newspaper & Periodical Storage | 15000 | Newspaper & Periodical Storage | Direct Procurement | Supplies | 15000 | 2023-04-11 | 14 April 2023 | 18 April 2023 | 20 April 2023 | 24 April 2023 | 25 April 2023 | 31 March 2024 | 08 April 2025
Shredding Machine | 30000 | Shredding Machine | Micro procurement | Supplies | 30000 | 2023-04-11 | 12 April 2023 | 13 April 2023 | 13 April 2023 | 13 April 2023 | 14 April 2023 | 25 April 2023 | N/A
Gazebos Assorted | 17800 | Gazebbos Burner | Micro procurement | Supplies | 17800 | 2023-06-22 | 26 June 2023 | 28 June 2023 | 28 June 2023 | 28 June 2023 | 29 June 2023 | 10 July 2023 | N/A
Public Address System | 10000 | Public Address System | Micro procurement | Supplies | 10000 | 2023-05-01 | 12 May 2023 | 17 May 2023 | 19 May 2023 | 23 May 2023 | 24 May 2023 | 09 June 2023 | N/A
Note and Coin Counting Machines | 105000 | Note and Coin Counting Machines | Quotations Proposal | Supplies | 105000 | 2023-05-01 | 12 May 2023 | 17 May 2023 | 19 May 2023 | 23 May 2023 | 24 May 2023 | 09 June 2023 | N/A
Office Equipment (Assorted) | 73500 | Office Equipment (Assorted) | Quotations Proposal | Supplies | 73500 | 2023-05-01 | 12 May 2023 | 17 May 2023 | 19 May 2023 | 23 May 2023 | 24 May 2023 | 09 June 2023 | N/A
Office Furniture (Assorted) | 766700 | Office Furniture (Assorted) | Quotations Proposal | Supplies | 766700 | 2023-05-01 | 12 May 2023 | 17 May 2023 | 19 May 2023 | 23 May 2023 | 24 May 2023 | 09 June 2023 | N/A
Total | 39336929.24 |  |  |  | 39336929.24
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Completed
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On Track
Note on M7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On Track
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On Track. To issue out ITT on the 14th and Closing on the 4th August 2023

## Expenses to Date
PROCUREMENT PLAN FINANCIAL YEAR 2023/2024
FINANCIAL YEAR: 2023 / 2024
Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
High Perfomance Culture Model | 340000 | High Perfomance Culture Model | Open Domestic Bidding | Service | 340000 | To be undertaken in Q2.
Customer Segmentation Model | 100000 | Customer Segmentation Model | Open Domestic Bidding | Service | 100000
Customer Loyalty Survey | 600000 | Customer Loyalty Survey | Open Domestic Bidding | Service | 600000
Process Mapping | 500000 | Process Mapping | Open Domestic Bidding | Service | 500000 | Mapping under way and on track. To be completed at the beginning of Q3.
Loan Pricing Model | 300000 | Loan Pricing Model | Selective | Service | 300000
King IV Governance Consultancy | 1000000 | King IV Governance Consultancy | Open Domestic Bidding | Service | 1000000 | 2023-06-09 | 2023-06-15 | 2023-06-26 | 2023-07-06 | 2023-07-07 | 2023-08-01 | To be completed at the end of Q2. Involves training.
Due Diligence Consultancy (Privatisation) | 1000000 | Due Diligence Consultancy (Privatisation) | Open Domestic Bidding | Service | 1000000
Agency Banking Marketing | 500000 | Agency Banking Marketing | Open Domestic Bidding | Service | 500000 | To be undertaken in Q2 and finalised in Q3. Currently have numerous campaigns running.
Insurance Agency Marketing | 250000 | Agency Banking Marketing | Open Domestic Bidding | Service | 250000
Total | 4590000 |  |  |  | 4590000